## Start Here
Contractor Job Cost & Cash Flow Tracker - FREE Edition (3 jobs)
Know which jobs make money before the job is over - not at tax time.
HOW TO USE (10 minutes)
1. Settings tab: enter your company name, opening cash balance, monthly overhead and start month.
2. Jobs tab: one row per job - contract value and your estimated cost by category.
3. Costs Log: every receipt, timesheet or sub invoice - date, job ID, category, amount.
4. Payments Log: every deposit or progress payment you receive from a client.
5. Job Dashboard and Cash Flow update automatically. Red = over budget or cash going negative.
COLOR LEGEND
Blue text = a value you type in. Black text = formula, do not overwrite. Green text = pulled from another tab.
Yellow fill = key setting you should review first.
Formula cells are locked so they can't be overwritten by accident. To change a formula: Review > Unprotect Sheet (no password).
The example rows (jobs J-101 to J-103 and their costs/payments) show the expected format. Overwrite or delete them.
UPGRADE TO PRO
PRO adds: 50 jobs, 1,000-row logs, a 12-month cash flow forecast with negative-cash warnings,
overhead allocation, estimate-vs-actual variance by category, and change-order tracking.
Get it here: [YOUR GUMROAD / LEMON SQUEEZY LINK]

## Settings
Setting | Value | Notes
Company name | Acme Renovations LLC | Shown on dashboards.
Opening cash balance ($) | 15000 | Bank balance on the start month's first day.
Monthly fixed overhead ($) | 1500 | Rent, insurance, truck, software, office salary. Example value - replace.
Target margin after overhead (%) | 10% | Jobs projected below this are flagged. Example value - set your own.
Forecast start month | 2026-01-01 | Enter the 1st day of a month.

## Jobs
Job ID | Client | Job description | Status | Start date | Contract value ($) | Change orders ($) | Est. labor ($) | Est. materials ($) | Est. subs ($) | Est. equipment ($) | Est. other ($) | Est. total cost ($) | Est. margin (%)
J-101 | Miller | Kitchen remodel | Active | 2026-01-05 | 48000 | 2500 | 14000 | 12000 | 6000 | 1200 | 800 | 34000 | 32.67%
J-102 | Okafor | Deck + pergola | Complete | 2026-01-12 | 22000 | 0 | 6500 | 7000 | 0 | 600 | 400 | 14500 | 34.09%
J-103 | Chen | Basement finish | Active | 2026-02-02 | 61000 | 0 | 18000 | 14000 | 11000 | 1500 | 1000 | 45500 | 25.41%
Note on G1: Approved change orders added to the contract value.

## Costs Log
Date | Job ID | Category | Vendor / worker | Description | Amount ($)
2026-01-08 | J-101 | Materials | Home Depot | Cabinets deposit | 6200
2026-01-15 | J-101 | Labor | Crew payroll | Week 2 demo + framing | 4100
2026-01-14 | J-102 | Materials | 84 Lumber | Composite decking | 7400
2026-01-21 | J-102 | Labor | Crew payroll | Deck build | 6900
2026-02-03 | J-101 | Subcontractors | Spark Electric | Rough-in electrical | 3800
2026-02-10 | J-103 | Materials | ABC Supply | Drywall + insulation | 5200
2026-02-18 | J-101 | Labor | Crew payroll | Install cabinets | 5600
2026-03-04 | J-103 | Labor | Crew payroll | Framing | 6100

## Payments Log
Date | Job ID | Invoice # | Note | Amount received ($)
2026-01-05 | J-101 | INV-001 | Deposit 30% | 14400
2026-01-12 | J-102 | INV-002 | Deposit 50% | 11000
2026-01-30 | J-102 | INV-003 | Final | 11000
2026-02-02 | J-103 | INV-004 | Deposit 25% | 15250
2026-02-20 | J-101 | INV-005 | Progress 40% | 19200

## Job Dashboard
Acme Renovations LLC - Job Dashboard
Job ID | Client | Status | Contract + COs ($) | Est. cost ($) | Actual cost ($) | % of budget used | Received ($) | Profit so far ($) | Margin if job ended now (%) | Flag
J-101 | Miller | Active | 50500 | 34000 | 19700 | 57.94% | 33600 | 13900 | 32.67% | OK
J-102 | Okafor | Complete | 22000 | 14500 | 14300 | 98.62% | 22000 | 7700 | 34.09% | OK
J-103 | Chen | Active | 61000 | 45500 | 11300 | 24.84% | 15250 | 3950 | 25.41% | OK