## Start Here
Contractor Job Cost & Cash Flow Tracker - PRO Edition
Know which jobs make money before the job is over - not at tax time.
HOW TO USE (10 minutes)
1. Settings tab: enter your company name, opening cash balance, monthly overhead and start month.
2. Jobs tab: one row per job - contract value and your estimated cost by category.
3. Costs Log: every receipt, timesheet or sub invoice - date, job ID, category, amount.
4. Payments Log: every deposit or progress payment you receive from a client.
5. Job Dashboard and Cash Flow update automatically. Red = over budget or cash going negative.
COLOR LEGEND
Blue text = a value you type in. Black text = formula, do not overwrite. Green text = pulled from another tab.
Yellow fill = key setting you should review first.
The example rows (jobs J-101 to J-103 and their costs/payments) show the expected format. Overwrite or delete them.

## Settings
Setting | Value | Notes
Company name | Acme Renovations LLC | Shown on dashboards.
Opening cash balance ($) | 15000 | Bank balance on the start month's first day.
Monthly fixed overhead ($) | 1500 | Rent, insurance, truck, software, office salary. Example value - replace.
Target margin after overhead (%) | 10% | Jobs projected below this are flagged. Example value - set your own.
Forecast start month | 2026-01-01 | Enter the 1st day of a month.

## Jobs
Job ID | Client | Job description | Status | Start date | Contract value ($) | Change orders ($) | Est. labor ($) | Est. materials ($) | Est. subs ($) | Est. equipment ($) | Est. other ($) | Est. total cost ($) | Est. margin (%)
J-101 | Miller | Kitchen remodel | Active | 2026-01-05 | 48000 | 2500 | 14000 | 12000 | 6000 | 1200 | 800 | 34000 | 32.67%
J-102 | Okafor | Deck + pergola | Complete | 2026-01-12 | 22000 | 0 | 6500 | 7000 | 0 | 600 | 400 | 14500 | 34.09%
J-103 | Chen | Basement finish | Active | 2026-02-02 | 61000 | 0 | 18000 | 14000 | 11000 | 1500 | 1000 | 45500 | 25.41%
Note on G1: Approved change orders added to the contract value.

## Costs Log
Date | Job ID | Category | Vendor / worker | Description | Amount ($)
2026-01-08 | J-101 | Materials | Home Depot | Cabinets deposit | 6200
2026-01-15 | J-101 | Labor | Crew payroll | Week 2 demo + framing | 4100
2026-01-14 | J-102 | Materials | 84 Lumber | Composite decking | 7400
2026-01-21 | J-102 | Labor | Crew payroll | Deck build | 6900
2026-02-03 | J-101 | Subcontractors | Spark Electric | Rough-in electrical | 3800
2026-02-10 | J-103 | Materials | ABC Supply | Drywall + insulation | 5200
2026-02-18 | J-101 | Labor | Crew payroll | Install cabinets | 5600
2026-03-04 | J-103 | Labor | Crew payroll | Framing | 6100

## Payments Log
Date | Job ID | Invoice # | Note | Amount received ($)
2026-01-05 | J-101 | INV-001 | Deposit 30% | 14400
2026-01-12 | J-102 | INV-002 | Deposit 50% | 11000
2026-01-30 | J-102 | INV-003 | Final | 11000
2026-02-02 | J-103 | INV-004 | Deposit 25% | 15250
2026-02-20 | J-101 | INV-005 | Progress 40% | 19200

## Job Dashboard
Acme Renovations LLC - Job Dashboard
Job ID | Client | Status | Contract + COs ($) | Est. cost ($) | Actual labor ($) | Actual materials ($) | Actual subcontractors ($) | Actual equipment ($) | Actual other ($) | Actual cost ($) | % of budget used | Labor variance ($) | Materials variance ($) | Received ($) | Outstanding to bill ($) | Profit so far ($) | Overhead share ($) | Projected net margin (%) | Flag
J-101 | Miller | Active | 50500 | 34000 | 9700 | 6200 | 3800 | 0 | 0 | 19700 | 57.94% | 4300 | 5800 | 33600 | 16900 | 13900 | 6808.9888 | 19.19% | OK
J-102 | Okafor | Complete | 22000 | 14500 | 6900 | 7400 | 0 | 0 | 0 | 14300 | 98.62% | -400 | -400 | 22000 | 0 | 7700 | 2966.2921 | 20.61% | OK
J-103 | Chen | Active | 61000 | 45500 | 6100 | 5200 | 0 | 0 | 0 | 11300 | 24.84% | 11900 | 8800 | 15250 | 45750 | 3950 | 8224.7191 | 11.93% | OK
TOTAL |  |  | 133500 | 94000 | 22700 | 18800 | 3800 | 0 | 0 | 45300 |  | 15800 | 14200 | 70850 | 62650 | 25550 | 18000
Note on R3: 12 months of Settings overhead, split across non-Bidding jobs by contract value.

## Cash Flow
Acme Renovations LLC - 12-Month Cash Flow
Month | Cash in: client payments ($) | Cash out: job costs ($) | Cash out: overhead ($) | Net cash flow ($) | Ending cash balance ($) | Warning
2026-01-01 | 36400 | 24600 | 1500 | 10300 | 25300
2026-02-01 | 34450 | 14600 | 1500 | 18350 | 43650
2026-03-01 | 0 | 6100 | 1500 | -7600 | 36050
2026-04-01 | 0 | 0 | 1500 | -1500 | 34550
2026-05-01 | 0 | 0 | 1500 | -1500 | 33050
2026-06-01 | 0 | 0 | 1500 | -1500 | 31550
2026-07-01 | 0 | 0 | 1500 | -1500 | 30050
2026-08-01 | 0 | 0 | 1500 | -1500 | 28550
2026-09-01 | 0 | 0 | 1500 | -1500 | 27050
2026-10-01 | 0 | 0 | 1500 | -1500 | 25550
2026-11-01 | 0 | 0 | 1500 | -1500 | 24050
2026-12-01 | 0 | 0 | 1500 | -1500 | 22550
TOTAL | 70850 | 45300 | 18000 | 7550
Tip: add expected future payments (with a future date) to the Payments Log to turn this into a forecast. Remove them if the client pays late.
Formulas:
Cash in: client payments ($) = SUMIFS('Payments Log'!$E2:E1001,'Payments Log'!$A2:A1001,">="&[Month],'Payments Log'!$A2:A1001,"<"&EDATE([Month],1))
Cash out: job costs ($) = SUMIFS('Costs Log'!$F2:F1001,'Costs Log'!$A2:A1001,">="&[Month],'Costs Log'!$A2:A1001,"<"&EDATE([Month],1))